## 1. H&S Action Tracker
Owner | Ref | Finding | Risk Rating | Recommendation | Managers Response | Officer Responsible | Deadline | Completed | Number of Days Left | Status | Actioned by | Actioned date | Legislation Requirements | Area of Risk | Recommendation first identified
Policy | R1 | The Health and Safety Law posters are displayed in the School; the posters located around School are not currently displaying the correct contact information. | Low | It is recommended that all Health and Safety Law posters within School display the correct Trade Union contact information as shown below. Health and Safety Representative Jason Horan – Lead Trade Union Health and Safety Rep 01925 442187 jhoran@warrington.gov.uk Other Health and Safety contacts Community Safety and Resilience Team 01925 442174 CEXhealth&safety@warrington.gov.uk This is good practice | The posters will be checked and adjustments made to any posters not carrying the correct information | Headteacher | This will be completed over the summer holiday ready for our return on 3rd September 2018 | Completed | #VALUE! | #VALUE! | PK | 2018-09-03 | Good Practice Health and Safety Information for Employees Regulations (HSIER) 1989 | Key Area of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Competency | R2 | The Assistant Head Teacher and the Administrative Assistant have both attended HABC level Managing Health and Safely training, this training was undertaken over 5 years ago. | Low | It is recommended that the Assistant Head Teacher and the Administrative Assistant attend a one day refresher training course for the HABC level 3 Managing Health and Safety. This is good practice | These two members of staff will be booked onto training as soon as it becomes available. | Headteacher | The Deputy Headteacher and Assistant Headteacher have boith gained the Level 3 award in February 2019. | Completed - February 2019 | #VALUE! | #VALUE! |  | 2018-09-03 | Good Practice Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999 | Key Area of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Planning & Implementing Risk Assessment | R3 | During the audit it was identified that there were no risk assessments in place to cover the tasks when using hand tools and work equipment etc. risk assessments are required in school for the tasks carried out by the Maintenance Officer and other staff in school. | Medium | It is recommended that there is the development of risk assessments for the tasks completed by staff in school, these risk assessments should be task specific. This is a statutory requirement. | All staff will undertake task based risk assessments in September 2018. | Headteacher | The training was delivered on 03/09/2018 by Adele Partridge. | Completed | #VALUE! | #VALUE! |  | 2018-09-03 | Legislative Non Compliance Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999 | Key Area of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Manual Handling operations | R4 | It was identified during the audit that there are members of staff in school that are required to undertake manual handling for people, who have not reviewed Manual Handling training since February 2015. | Medium | It is recommended that refresher training for staff who are required to carry out manual handling for people is completed every 3 years of sooner if identified by the risk assessment process or deemed necessary by staff This is a statutory requirement. | The Manintenance Officer will carry out task based risk assessments for equipment used around school. | Maintenance Officer | Training delivered by Jo Milnes on 03/09/2018 | Completed March 2019 | #VALUE! | #VALUE! |  | 2018-09-03 | Legislative Non Compliance Management of Health and Safety at Work Regulations 1999 Manual Handling Operation Regulations 1992. | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Manual Handling operations | R5 | It was identified during the audit that the Site Manager and the Caretaker last attended manual handling training over 3 years ago. | Medium | It is recommended that the Maintenance Officer attends a manual handling course to cover the manual handling activities he carries out as part of his duties. (Note no record of attendance on manual handling training course on the School SIMS report). This is a statutory requirement. | The Maintenace Officer and Caretaker will be booked onto Manual Handling training for the autumn term 2018. | Headteacher | Amy Bradley will organise the training in earlt September 2018. Amy was contacted by text on 30/07/2018. | CompletedNew Maintenance Officer has upto date certificates | #VALUE! | #VALUE! |  | MO looking for course. | Legislative Non Compliance Management of Health and Safety at Work Regulations 1999 Manual Handling Operation Regulations 1992. | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Manual Handling operations | R6 | There is no specific manual handling risk assessment for the manual handling tasks carried out by the Maintenance Officer. | Medium | It is recommended that a specific manual handling risk assessment be undertaken for the tasks carried out by the Management Officer, this should include the task being undertaken; the individuals capabilities; the loads being lifted or moved and the environmental conditions. This is a statutory requirement. | The Manintenance Officer will be requested to carry out task based risk assessments for manual handling activities. | Maintenace Officer | A new Maintenance was employed by the school from 01/01/2019. He will receive all the necessary training as soon as we can book him onto a course. | Completed | #VALUE! | #VALUE! |  | Will be completed once training has been undertaken. | Legislative Non Compliance Management of Health and Safety at Work Regulations 1999 Manual Handling Operation Regulations 1992. | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Accident Reporting & Investigation | R7 | A number of staff attended defibrillator training in 2014. | Low | It is recommended that staff attend refresher defibrillator training as it is 4 years since staff were trained in the use of the schools defibrillator. (We recommend that defibrillator training is refreshed annually). This is good practice. | Amy Bradley (TA responsible for medical risk assessments) will organise deffirillator training for staff early in September 2018. | Amy Bradley | See above. | Ongoing | #VALUE! | #VALUE! |  |  | Good Practice Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999 | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Management of Stress | R8 | The schools stress risk assessment has not been reviewed since 2014. | Low | It is recommended that the team stress risk assessment is reviewed; the updated stress risk assessment should be shared with all relevant staff members. This is a statutory requirement | The Headteacher met with all staff to discuss the team stress risk assessment on. All staff were encouraged to speak privately with the Headteacherif there were still any areas of concern. There will be a new staff stress risk assessment produced over the summmer period and distributed to all staff. | Headteacher | Headteacher will write a new stafff stress risk assessment ready for the new term in September. | Completed | #VALUE! | #VALUE! |  | Completed August 2018. | Legislative Non Compliance Health and Safety at Work Act 1974 Management of Health and Safety at Work | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Management of Stress | R9 | We were advised that no members of staff within school have attended training in how to identify and manage stress in your team. | Low | It is recommended that a member of the schools senior leadership team should consider undertaking the training course on how to identify and manage stress in your team. Good practice | The Headteacher will commission Adele Partridge to deliver training to all membes of the SLT in identifying and managing stress. | Headteacher | We will organise the training for the Autumn term 2018. | To do | #VALUE! | #VALUE! |  | One of the SLT will go on a training course when available. | Good Practice Health and Safety at Work Act 1974 Management of Health and Safety at Work | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Control of Substances Hazardous to Health (COSHH) | R10 | The COSHH risk assessments have not been reviewed since January 2015. | Low | It is recommended that the COSHH risk assessments are reviewed by the Maintenance Officer to ensure that the control measures are still relevant and up to date. This is a statutory requirement. | Maintenance Officer will review all the COSHH risk assessments. | Maintenance Officer. | Maintenance Officer will have reviewed all COSHH risk assessments by the start of the new school term in September 2018. | Completed | #VALUE! | #VALUE! |  | COSSH RA has been updated and signed off by cleaning staff. | Legislative Non Compliance Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999 The Control of Substances Hazardous to Health 2002 (as amended 2004) | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Provision and Use of Work Equipment (PUWER) | R11 | There was some evidence to demonstrate that risks from work equipment have been assessed for equipment used within the school. | Medium | It is recommended that specific risk assessments for work equipment used by the Maintenance Officer and other staff are undertaken or reviewed, to ensure all equipment is included and appropriate controls are in place for the selection, inspection, maintenance and use of the equipment. (i.e. PAT testing equipment, mobile tower scaffold, use of ladders, hand tools, etc.) This is a statutory requirement. | See Recommendation 3 above.+ | Maintenance Officer | Maintenance Officer will have review all work equipment risk assessments. | Completed | #VALUE! | #VALUE! |  | Use of portable power tools completed September 2018. Cleaning staff have read and signed the document. | Legislative Non Compliance Management of Health and Safety at Work Regulations 1999 Provision and Use of Work Equipment Regulations 1998 | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Legionella | R12 | No up to date legionella control management plan in place for the school | Medium | It is recommended that the legionella control management plan is fully completed and shared with appropriate staff in school. This is good practice | The legionella management plan will be reviewed and updated for September 2018. | Headteacher | Headteacher will carry out a review and update the legionella management plan where needed. | Completed - March 2019 | #VALUE! | #VALUE! |  | Updated for September 2018 | Good Practice ACoP L 8 2013 The Control of Substances Hazardous to Health Regulations 2002 | Key Area of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Asbestos | R13 | The school did not have a fully completed Asbestos Management Plan, which should detail how risks from asbestos containing material are to be managed within School. | Medium | It is recommended that the Asbestos Management Plan is fully completed and once completed it should be shared with all staff. This is a statutory requirement | The asbestos management plan will be reviewed and updated for September 2018. | Headteacher | Headteacher will carry out a review and update the asbestos management plan where needed. | Completed March 2019 | #VALUE! | #VALUE! |  | Update for September 2018 | Legislative Non Compliance The Control of Asbestos Regulations 2012 | Key Area of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Asbestos | R14 | Key members of staff have not attended asbestos awareness training | Medium | It is recommended that relevant staff in school attend asbestos awareness training. This is a statutory requirement | Key members of staff who are named on the asbestos management plan will update their training. | Headteacher | Headteacher will ensure all staff who require updates to their asbestos management training will receive it in the autumn term 2018. | Ongoing | #VALUE! | #VALUE! |  | All relevant staff have now completed training. | Legislative Non Compliance Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999 The Control of Asbestos at Work Regulations 2013 | Key Area of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Management of Fire and other emergency situations | R15 | There is only one member of staff in school that has attended fire warden training. | Medium | It is recommended that a number of staff are identified in school to attend Fire Warden Training to ensure appropriate cover if the Head Teacher is not available on site. This training is available at St Werburghs Training Centre Tel no. 442600. This is a statutory requirement. | Eight members of staff received Fire Warden training on Friday 29th June 2018. The training was delivered by Adele Partridge. | Headteacher | This information was passed on during the H&S review. | Completed - 25/06/18 | #VALUE! | #VALUE! |  | Completed 29/05/2018 | Legislative Non compliance Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999 The Regulatory Reform Fire Safety Order 2005. | Key Area of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Workplace Health, Safety & Welfare | R16 | There is no weekly inspection checklist used by the Maintenance Officer to record his findings. | Low | It is recommended that a weekly inspection checklist is used by the Maintenance Officer to record the weekly visual checks around the school that are carried out, for the schools audit trail. Good practice | The Headteacher and Maintenace Officer will jointly produce a visual checklist that will be signed off weekly. | Headteacher / Maintenance Officer | New checklists in use from January 2019. | New checklists in use from January 2019. | #VALUE! | #VALUE! |  | Document produced and signed from 03/09/2018 | Good Practice Health and Safety at Work Act 1974 Workplace Health Safety and Welfare Regulations 1992 | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Workplace Health, Safety & Welfare | R17 | Various fragile roofs identified with no signage in place. | Low | It is recommended that fragile roof signs are purchased and displayed at various points around the school site where access can be gained to the various canopy covered outdoor play areas. This is a statutory requirement. | Quotes for the signs have been received. | Headteacher / Maintenance Officer | The Headteacher agreed to the quote on 30/07/2018 and instructed the Maintenace Officer to place the order. The signs will be fitted before the start of the autumn term. | Completed - please note that manufaturers have advised that fragile roof signs are not required. | #VALUE! | #VALUE! |  | Signs in place - 03/09/2018 | Legislative Non Compliance Management of Health and Safety at Work Regulations 1999 Health and Safety (Safety, Signs and Signals) Regulations 1996. | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Workplace Health, Safety & Welfare | R18 | Fire action signs not displayed at all break glass call points around the school. | Low | It is recommended that fire action signs are purchased and displayed at the break glass call points in the sports hall area of the school site. This is a statutory requirement. | Quotes for the signs have been received. | Headteacher / Maintenance Officer | The Headteacher agreed to the quote on 30/07/2018 and instructed the Maintenace Officer to place the order. The signs will be fitted before the start of the autumn term. | Completed | #VALUE! | #VALUE! |  | When signs have been purchased the MO will fix. | Legislative Non Compliance Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999, | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Workplace Health, Safety & Welfare | R19 | Boiler room untidy on the day of the audit. | Low | It is recommended that the boiler room is kept tidy to prevent slip, trip and fall accidents to staff and contractors who need to work in this area. This is good practice | The Headteacher has spoken with Peter Turner from Green Lane and Gary Hall froom Fox Wood about keeping the boiler room tidy and free from slip, trip and fall accidents. | Headteacher. Maintenance Officers from Green Lane and Fox Wood Schools | Boiler room will be tidied over the summer break. | Completed | #VALUE! | #VALUE! |  | Cleaned during summer break 2018. | Good Practice Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999, | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Workplace Health, Safety & Welfare | R20 | The plant room equipment and chemical dosing system for the hydro therapy pool is located in Green Lane School boiler room. | Low | It is recommended that the eye wash station is relocated as it was positioned above the pool automatic dosing system where a leak could occur. During a incident you would have to reach across the dosing system to access the eyewash. (This recommendation was discussed on the day of the audit with Gary Hall the Maintenance Officer of Fox Wood School who has the responsibility for the management of the hydro therapy pool). This is good practice | Paul King will pass this on to Lucinda Duffy, Headteacher of Fox Wood School. | Maintenance Officers from Fox Wood School. | Gary Hall will be asked to discuss this with the Headteacher of Fox Wood School. | Completed | #VALUE! | #VALUE! |  | Passed on to Fox Wood MO | Good Practice Health and Safety at Work Act 1974 Management of Health and Safety at Work Regulations 1999, | Other Areas of Risk | Health and Safety Audit carried out on 25/06/2018 and 05/07/2018.
Formulas:
Number of Days Left = IF([Completed]="Yes","",[Deadline]-TODAY())

## 2. Pivot Summary
Green Lane School H&S Audit - Action Tracker
H&S Audit - Action Tracker
Count of Recommendations
|  | #VALUE! | Grand Total
Provision and Use of Work Equipment (PUWER) | Medium | 1 | 1
| Medium Total | 1 | 1
Provision and Use of Work Equipment (PUWER) Total |  | 1 | 1
Legionella | Medium | 1 | 1
| Medium Total | 1 | 1
Legionella Total |  | 1 | 1
Asbestos | Medium | 2 | 2
| Medium Total | 2 | 2
Asbestos Total |  | 2 | 2
Management of Fire and other emergency situations | Medium | 1 | 1
| Medium Total | 1 | 1
Management of Fire and other emergency situations Total |  | 1 | 1
Workplace Health, Safety & Welfare | Low | 5 | 5
| Low Total | 5 | 5
Workplace Health, Safety & Welfare Total |  | 5 | 5
Policy | Low | 1 | 1
| Low Total | 1 | 1
Policy Total |  | 1 | 1
Competency | Low | 1 | 1
| Low Total | 1 | 1
Competency Total |  | 1 | 1
Planning & Implementing Risk Assessment | Medium | 1 | 1
| Medium Total | 1 | 1
Planning & Implementing Risk Assessment Total |  | 1 | 1
Manual Handling operations | Medium | 3 | 3
| Medium Total | 3 | 3
Manual Handling operations Total |  | 3 | 3
Accident Reporting & Investigation | Low | 1 | 1
| Low Total | 1 | 1
Accident Reporting & Investigation Total |  | 1 | 1
Management of Stress | Low | 2 | 2
| Low Total | 2 | 2
Management of Stress Total |  | 2 | 2
Control of Substances Hazardous to Health (COSHH) | Low | 1 | 1
| Low Total | 1 | 1
Control of Substances Hazardous to Health (COSHH) Total |  | 1 | 1
Grand Total |  | 20 | 20
This shape represents a slicer. Slicers can be used in at least Excel 2010.If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010.If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010.If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010.If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010.If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.